## EXAMPLE
How long should my recruitment take?
This document provides an example of how long a recruitment campaign may take. As hiring managers you can use the recruitment timeline calculator, to help with your recruitment planning.
OPTION 1 - NADIA; DEPARTMENT MANAGER |  |  |  | NOTES
Nadia has received a resignation from one of her team. She is able to begin recruiting to a replacement post immediately, and has used the recruitment planner to give her an indication of how long the recruitment may take.
Date I am able to start recruiting: | Days |  | 2019-02-05
Create recruitment plan | 2 | days | 2019-02-07
Appoint a hiring panel | 1 | day | 2019-02-08
Prepare details about the role | 5 | days | 2019-02-13
> Job description
> Person Specification
> Draft Advert
> Decide on external advertising (if required)
Upload vacancy and submit first fund check on e-recruitment system | 1 | day | 2019-02-14
Obtain first find check approval, from FPA Manager | 3 | days | 2019-02-17
HR review all recruitment documents and publish | 3 | days | 2019-02-20
Advertise role (time period as per hiring manager request) | 28 | days | 2019-03-20
Panel shortlisting | 2 | days | 2019-03-22
Interview prep, invitations sent, notice to candidate | 7 | days | 2019-03-29
Interviews | 2 | days | 2019-03-31
Decision making | 1 | days | 2019-04-01
Conditional offer made | 1 | days | 2019-04-02
Conditional offer accepted and start date agreed | 2 | days | 2019-04-04
Notice period (dependant on successful candidate) | 30 | days | 2019-05-04
Earliest employee start date: |  |  | 2019-05-04
OPTION 2 - SIMON; TEAM LEADER |  |  |  | NOTES
Simon has an event taking place over the Summer Term. He needs to recruit 4 administrators to the team in order to manage the additional administration that will come to his team. He is looking for the new hires to start in early May 2019 so that new recruits are trained and up to speed before the event on the 22 May 2019.
Date I would like the vacancy filled by: | Days |  | 2019-05-06
Create recruitment plan | 2 | days | 2019-02-03
Appoint a hiring panel | 1 | day | 2019-02-05
Prepare details about the role | 5 | days | 2019-02-06
> Job description
> Person Specification
> Draft Advert
> Decide on external advertising (if required)
Upload vacancy and submit first fund check on e-recruitment system | 1 | day | 2019-02-11
Obtain e-recruit approval | 9 | days | 2019-02-12
Advertise role (time period as per hiring manager request) | 14 | days | 2019-02-21
Shortlisting | 2 | days | 2019-03-07
Interview prep, invitations sent, notice to candidate | 13 | days | 2019-03-09
Interviews | 1 | day | 2019-03-22
Decision making | 2 | days | 2019-03-23
Conditional offer made | 2 | days | 2019-03-25
Conditional offer accepted and start date agreed | 10 | days | 2019-03-27
Notice period (dependant on successful candidate) | 30 | days | 2019-04-06
Recommended date to start recruiting: |  |  | 2019-02-03
Last updated: 08/03/2019